## Full experimental plan
Step | Step Description | Axial Pressure (psi) | Radial Pressure (psi) | S3/S1 (=0.8) | Pore Pressure (psi) | P/S3 (=0.5) | Effective Stress (psi) | Time (hrs) | Cumulative Time (hrs) | Delta P for flow | Delta P/P | k test - Upstream Pressure (psi) | k test - Downstream Pressure (psi) | Measurements | Notes
1.1 | Apply axial load | 100 | 0 | 0 | 0 |  | 0 | 24 | 24
1.2 | Apply radial load | 100 | 100 | 1 | 0 | 0 | 100 | 24 | 48 | [5 empty] | sealing should be achieved at this pressure
1.3 | Raise Pore Pressure | 100 | 100 | 1 | 20 | 0.2 | 80 | 0.8 | 48.8 | [5 empty] | check for sealing - connection between pore and radial pressures
1.4 | Flush core | 100 | 100 | 1 | 20 | 0.2 | 80 | 3 | 51.8 | 20 | 1 | 30 | 10 | k | wait for flowrate to become constant to end step
1.5 | Attain desired effective stress for saturation | 145 | 145 | 1 | 20 |  | 125 | [7 empty] | Back pressure of 125 psi
2.1 | Back Pressure saturation ramp | 250 | 250 | 1 | 125 | 0.5 | 125 | 6 | 57.8 |  |  |  |  | Potentiometer, Vp, Vs | Maintain constant effective stress, keep drains closed
2.2 | Desired effective stress for saturation - anisotropic loading | 312.5 | 250 | 0.8 | 125 | 0.5 | 125 | 2.5 | 60.3 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 312.5 | 250 | 0.8 | 125 | 0.5 | 125 | 0.5 | 60.8 | 25 | 0.2 | 137.5 | 112.5 |  | Make flow input/output pressure = pore pressure, then setup ramps
2.4 | Permeability test | 312.5 | 250 | 0.8 | 125 | 0.5 | 125 | 8 | 68.3 | 25 | 0.2 | 137.5 | 112.5 | k | Initial Permeability test, Delta P/ P =0.5
2.5 | Unloading | 312.5 | 250 | 0.8 | 200 | 0.8 | 50 | 3 | 71.3 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 312.5 | 250 | 0.8 | 200 | 0.8 | 50 | 0.5 | 71.8 | 25 | 0.125 | 212.5 | 107.05 |  | Make flow input/output pressure = pore pressure, then setup ramps
2.7 | Permeability test | 312.5 | 250 | 0.8 | 200 | 0.8 | 50 | 8 | 79.3 | 25 | 0.125 | 212.5 | 107.05 | k | Pore pressure increased, reduce Delta P for k test
2.8 | Draining | 312.5 | 250 | 0.8 | 125 | 0.5 | 125 | 3 | 82.3 |  |  |  |  | Potentiometer, Vp, Vs
3.1 | Make isotropic stress state for loading | 312.5 | 312.5 | 1 | 156.25 | 0.5 | 156.25 | 2.5 | 84.8 |  |  |  |  | Potentiometer, Vp, Vs | Attain isotropic stress state for loading
3.2 | Loading - Isotropic | 750 | 750 | 1 | 375 | 0.5 | 375 | 17.5 | 102.3 |  |  |  |  | Potentiometer, Vp, Vs | Axial and Radial Ramping
3.3 | Loading - Anisotropic | 937.5 | 750 | 0.8 | 375 | 0.5 | 375 | 7.5 | 109.8 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 937.5 | 750 | 0.8 | 375 | 0.5 | 375 | 1.5 | 111.3 | 75 | 0.2 | 412.5 | 337.5 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.4 | Permeability test | 937.5 | 750 | 0.8 | 375 | 0.5 | 375 | 8 | 117.8 | 75 | 0.2 | 412.5 | 337.5 | k | Initial Permeability test, Delta P/ P =0.5
3.5 | Unloading | 937.5 | 750 | 0.8 | 525 | 0.7 | 225 | 6 | 123.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 937.5 | 750 | 0.8 | 525 | 0.7 | 225 | 1.5 | 125.3 | 75 | 0.14286 | 562.5 | 487.5 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.6 | Permeability test | 937.5 | 750 | 0.8 | 525 | 0.7 | 225 | 8 | 131.8 | 75 | 0.14286 | 562.5 | 487.5 | k | Pore pressure increased, reduce Delta P for k test
3.5 | Unloading | 937.5 | 750 | 0.8 | 600 | 0.8 | 150 | 3 | 134.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 937.5 | 750 | 0.8 | 600 | 0.8 | 150 | 1.5 | 136.3 | 75 | 0.125 | 637.5 | 562.5 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.6 | Permeability test | 937.5 | 750 | 0.8 | 600 | 0.8 | 150 | 8 | 142.8 | 75 | 0.125 | 637.5 | 562.5 | k | Pore pressure increased, reduce Delta P for k test
3.7 | Draining | 937.5 | 750 |  | 375 | 0.5 | 375 | 9 | 151.8 |  |  |  |  | Potentiometer, Vp, Vs
3.1 | Make isotropic stress state for loading | 937.5 | 937.5 | 1 | 468.75 | 0.5 | 468.75 | 7.5 | 159.3 |  |  |  |  | Potentiometer, Vp, Vs | Attain isotropic stress state for loading
3.2 | Loading - Isotropic | 1500 | 1500 | 1 | 750 | 0.5 | 750 | 22.5 | 181.8 |  |  |  |  | Potentiometer, Vp, Vs | Axial and Radial Ramping
3.3 | Loading - Anisotropic | 1875 | 1500 | 0.8 | 750 | 0.5 | 750 | 15 | 196.8 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 1875 | 1500 | 0.8 | 750 | 0.5 | 750 | 3 | 199.8 | 150 | 0.2 | 825 | 675 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.4 | Permeability test | 1875 | 1500 | 0.8 | 750 | 0.5 | 750 | 8 | 204.8 | 150 | 0.2 | 825 | 675 | k | Initial Permeability test, Delta P/ P =0.5
3.5 | Unloading | 1875 | 1500 | 0.8 | 975 | 0.65 | 525 | 9 | 213.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 1875 | 1500 | 0.8 | 975 | 0.65 | 525 | 3 | 216.8 | 150 | 0.15385 | 1050 | 900 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.6 | Permeability test | 1875 | 1500 | 0.8 | 975 | 0.65 | 525 | 8 | 221.8 | 150 | 0.15385 | 1050 | 900 | k | Pore pressure increased, reduce Delta P for k test
3.7 | Unloading | 1875 | 1500 | 0.8 | 1200 | 0.8 | 300 | 9 | 230.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 1875 | 1500 | 0.8 | 1200 | 0.8 | 300 | 3 | 233.8 | 150 | 0.125 | 1275 | 1125 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.8 | Permeability test | 1875 | 1500 | 0.8 | 1200 | 0.8 | 300 | 8 | 238.8 | 150 | 0.125 | 1275 | 1125 | k | Pore pressure increased, reduce Delta P for k test
3.9 | Unloading | 1875 | 1500 | 0.8 | 1350 | 0.9 | 150 | 6 | 244.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 1875 | 1500 | 0.8 | 1350 | 0.9 | 150 | 3 | 247.8 | 150 | 0.11111 | 1425 | 1275 |  | Make flow input/output pressure = pore pressure, then setup ramps
3.1 | Permeability test | 1875 | 1500 | 0.8 | 1350 | 0.9 | 150 | 8 | 252.8 | 150 | 0.11111 | 1425 | 1275 | k | Pore pressure increased, reduce Delta P for k test
3.11 | Draining | 1875 | 1500 |  | 750 | 0.5 | 750 | 24 | 276.8 |  |  |  |  | Potentiometer, Vp, Vs
4.1 | Make isotropic stress state for loading | 1875 | 1875 | 1 | 937.5 | 0.5 | 937.5 | 15 | 291.8 |  |  |  |  | Potentiometer, Vp, Vs | Attain isotropic stress state for loading
4.2 | Loading - Isotropic | 2500 | 2500 | 1 | 1250 | 0.5 | 1250 | 25 | 316.8 |  |  |  |  | Potentiometer, Vp, Vs | Axial and Radial Ramping
4.3 | Loading - Anisotropic | 3125 | 2500 | 0.8 | 1250 | 0.5 | 1250 | 25 | 341.8 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 3125 | 2500 | 0.8 | 1250 | 0.5 | 1250 | 5 | 346.8 | 250 | 0.2 | 1375 | 1125 |  | Make flow input/output pressure = pore pressure, then setup ramps
4.4 | Permeability test | 3125 | 2500 | 0.8 | 1250 | 0.5 | 1250 | 8 | 349.8 | 250 | 0.2 | 1375 | 1125 | k | Initial Permeability test, Delta P/ P =0.5
4.5 | Unloading | 3125 | 2500 | 0.8 | 1625 | 0.65 | 875 | 15 | 364.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 3125 | 2500 | 0.8 | 1625 | 0.65 | 875 | 5 | 369.8 | 250 | 0.15385 | 1750 | 1500 |  | Make flow input/output pressure = pore pressure, then setup ramps
4.6 | Permeability test | 3125 | 2500 | 0.8 | 1625 | 0.65 | 875 | 8 | 372.8 | 250 | 0.15385 | 1750 | 1500 | k | Pore pressure increased, reduce Delta P for k test
4.7 | Unloading | 3125 | 2500 | 0.8 | 2000 | 0.8 | 500 | 15 | 387.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 3125 | 2500 | 0.8 | 2000 | 0.8 | 500 | 5 | 392.8 | 250 | 0.125 | 2125 | 1875 |  | Make flow input/output pressure = pore pressure, then setup ramps
4.8 | Permeability test | 3125 | 2500 | 0.8 | 2000 | 0.8 | 500 | 8 | 395.8 | 250 | 0.125 | 2125 | 1875 | k | Pore pressure increased, reduce Delta P for k test
4.9 | Unloading | 3125 | 2500 | 0.8 | 2250 | 0.9 | 250 | 10 | 405.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 3125 | 2500 | 0.8 | 2250 | 0.9 | 250 | 5 | 410.8 | 250 | 0.11111 | 2375 | 2125 |  | Make flow input/output pressure = pore pressure, then setup ramps
4.1 | Permeability test | 3125 | 2500 | 0.8 | 2250 | 0.9 | 250 | 8 | 413.8 | 250 | 0.11111 | 2375 | 2125 | k | Pore pressure increased, reduce Delta P for k test
4.11 | Draining | 3125 | 2500 | 0.8 | 1250 | 0.5 | 1250 | 40 | 453.8 |  |  |  |  | Potentiometer, Vp, Vs
5.1 | Make isotropic stress state for loading | 3125 | 3125 | 1 | 1562.5 | 0.5 | 1562.5 | 25 | 478.8 |  |  |  |  | Potentiometer, Vp, Vs | Attain isotropic stress state for loading
5.2 | Loading - Isotropic | 3500 | 3500 | 1 | 1750 | 0.5 | 1750 | 15 | 493.8 |  |  |  |  | Potentiometer, Vp, Vs | Axial and Radial Ramping
5.3 | Loading - Anisotropic | 4375 | 3500 | 0.8 | 1750 | 0.5 | 1750 | 35 | 528.8 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 4375 | 3500 | 0.8 | 1750 | 0.5 | 1750 | 7 | 535.8 | 350 | 0.2 | 1925 | 1575 |  | Make flow input/output pressure = pore pressure, then setup ramps
5.4 | Permeability test | 4375 | 3500 | 0.8 | 1750 | 0.5 | 1750 | 8 | 536.8 | 350 | 0.2 | 1925 | 1575 | k | Initial Permeability test, Delta P/ P =0.5
5.5 | Unloading | 4375 | 3500 | 0.8 | 2275 | 0.65 | 1225 | 21 | 557.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 4375 | 3500 | 0.8 | 2275 | 0.65 | 1225 | 7 | 564.8 | 350 | 0.15385 | 2450 | 2100 |  | Make flow input/output pressure = pore pressure, then setup ramps
5.6 | Permeability test | 4375 | 3500 | 0.8 | 2275 | 0.65 | 1225 | 8 | 565.8 | 350 | 0.15385 | 2450 | 2100 | k | Pore pressure increased, reduce Delta P for k test
5.7 | Unloading | 4375 | 3500 | 0.8 | 2800 | 0.8 | 700 | 21 | 586.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 4375 | 3500 | 0.8 | 2800 | 0.8 | 700 | 7 | 593.8 | 350 | 0.125 | 2975 | 2625 |  | Make flow input/output pressure = pore pressure, then setup ramps
5.8 | Permeability test | 4375 | 3500 | 0.8 | 2800 | 0.8 | 700 | 8 | 594.8 | 350 | 0.125 | 2975 | 2625 | k | Pore pressure increased, reduce Delta P for k test
5.9 | Unloading | 4375 | 3500 | 0.8 | 3150 | 0.9 | 350 | 14 | 608.8 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 4375 | 3500 | 0.8 | 3150 | 0.9 | 350 | 7 | 615.8 | 350 | 0.11111 | 3325 | 2975 |  | Make flow input/output pressure = pore pressure, then setup ramps
5.1 | Permeability test | 4375 | 3500 | 0.8 | 3150 | 0.9 | 350 | 8 | 616.8 | 350 | 0.11111 | 3325 | 2975 | k | Pore pressure increased, reduce Delta P for k test
5.11 | Draining | 4375 | 3500 | 0.8 | 1750 | 0.5 | 1750 | 56 | 672.8 |  |  |  |  | Potentiometer, Vp, Vs
6.1 | Make isotropic stress state for loading | 4375 | 4375 | 1 | 2187.5 | 0.5 | 2187.5 | 35 | 707.8 |  |  |  |  | Potentiometer, Vp, Vs | Attain isotropic stress state for loading
6.2 | Loading - Isotropic | 4800 | 4800 | 1 | 2400 | 0.5 | 2400 | 17 | 724.8 |  |  |  |  | Potentiometer, Vp, Vs | Axial and Radial Ramping
6.3 | Loading - Anisotropic | 6000 | 4800 | 0.8 | 2400 | 0.5 | 2400 | 48 | 772.8 |  |  |  |  | Potentiometer, Vp, Vs | Achieve anisotropic stress state, ramp axial
2.6 | Permeability test ramp | 6000 | 4800 | 0.8 | 2400 | 0.5 | 2400 | 9.6 | 782.4 | 480 | 0.2 | 2640 | 2160 |  | Make flow input/output pressure = pore pressure, then setup ramps
6.4 | Permeability test | 6000 | 4800 | 0.8 | 2400 | 0.5 | 2400 | 8 | 780.8 | 480 | 0.2 | 2640 | 2160 | k | Initial Permeability test, Delta P/ P =0.5
6.5 | Unloading | 6000 | 4800 | 0.8 | 3120 | 0.65 | 1680 | 28.8 | 809.6 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 6000 | 4800 | 0.8 | 3120 | 0.65 | 1680 | 9.6 | 819.2 | 480 | 0.15385 | 3360 | 2880 |  | Make flow input/output pressure = pore pressure, then setup ramps
6.6 | Permeability test | 6000 | 4800 | 0.8 | 3120 | 0.65 | 1680 | 8 | 817.6 | 480 | 0.15385 | 3360 | 2880 | k | Pore pressure increased, reduce Delta P for k test
6.7 | Unloading | 6000 | 4800 | 0.8 | 3840 | 0.8 | 960 | 28.8 | 846.4 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 6000 | 4800 | 0.8 | 3840 | 0.8 | 960 | 9.6 | 856 | 480 | 0.125 | 4080 | 3600 |  | Make flow input/output pressure = pore pressure, then setup ramps
6.8 | Permeability test | 6000 | 4800 | 0.8 | 3840 | 0.8 | 960 | 8 | 854.4 | 480 | 0.125 | 4080 | 3600 | k | Pore pressure increased, reduce Delta P for k test
6.9 | Unloading | 6000 | 4800 | 0.8 | 4320 | 0.9 | 480 | 19.2 | 873.6 |  |  |  |  | Potentiometer, Vp, Vs
2.6 | Permeability test ramp | 6000 | 4800 | 0.8 | 4320 | 0.9 | 480 | 9.6 | 883.2 | 480 | 0.11111 | 4560 | 4080 |  | Make flow input/output pressure = pore pressure, then setup ramps
6.1 | Permeability test | 6000 | 4800 | 0.8 | 4320 | 0.9 | 480 | 8 | 881.6 | 480 | 0.11111 | 4560 | 4080 | k | Pore pressure increased, reduce Delta P for k test
6.11 | Draining | 6000 | 4800 | 0.8 | 2400 | 0.5 | 2400 | 76.8 | 958.4 |  |  |  |  | Potentiometer, Vp, Vs
Loading Rates
| Confining Pressure Ramping Rate | 25 psi/hr
| Pore Pressure Ramping Rate | 25 psi/hr
Flow through permeability test

## Details of steps
Make dry weight measurement of sample before putting into pressure veseel
During flow through test, both pumps are in mode 12 - const P bidirectional

## Experimental Plan
Step | Step Description | Axial Pressure (psi) | Radial Pressure (psi) | Time (hrs) | Cumulative Time (hrs) | Pore Pressure (psi) | Effective Stress (psi) | k test - Upstream Pressure (psi) | k test - Downstream Pressure (psi) | Measurements | Notes
1 | Apply axial load | 80 | 0 | 24 |  | 0 | 0 | No flow | No flow | Potentiometer | 75 psi is required to attain sealing of liner with endcaps
Lower stress application rate as there is no radial load
2 | Apply radial load | 80 | 80 | 24 |  | 0 | 80 | No flow | No flow | Initial Sample Length | Radial Pressure Ramping step
3 | Raise Pore Pressure | 80 | 80 | 2 |  | 5 | 75 | 10 | 0 | Potentiometer | Initial Pore Pressure Ramp
3.1 | Flush core | 80 | 80 | 5 |  | 5 | 75 | 10 | 0 |  | Initial flushing of core
Wait for flowrate to become constant on downstream end
4.1 | Initial Ramping to effective stress - isotropic | 185 | 185 | 7 |  | 50 | 135 | No flow | Noflow
4.2 | Initial Ramping to effective stress - anisotropic | 231.25 | 185 | [6 empty] | Potentiometer | Attain desired constant effective stress | Conduct B tests
[10 empty] | Vp, Vs | Close drainage valve
Pump pore fluid only from upstream side
Axial and Radial can be ramped simulataneously
5 | Initial loading and saturation | 312.5 | 250 | 8.5 |  | 115 | 135 | No flow | No flow | Vp, Vs | First Loading phase | Conduct B tests
[10 empty] | Potentiometer | Axial and Radial can be ramped simulataneously | Complete Saturation
Inject pore fluid only from upstream side
5.1 | Permeability | 312.5 | 250 | 5 |  | 115 | 135 | 142 | 88 | k | Permeability test - Gradient of 54 psi | End of Initial Loading
6 | Unloading | 250 | 250 |  |  | 150 | 100 | No flow | No flow | Vp,Vs | Pore fluid injection from both sides
Potentiometer
6.1 | Permeability test | 250 | 250 |  |  | 150 | 100 | 177 | 123 | k | Permeability test - Gradient of 54 psi
6.3 | Draining | 250 | 250 |  |  | 115 | 135 | No flow | No flow | Vp, Vs, Potentiometer
7.1 | Loading | 750 | 750 |  |  | 350 | 400 | No flow | No flow | Vp, Vs | Axial and Radial can be ramped simulataneously
[10 empty] | Potentiometer | Pore fluid injection from both sides
7.1 | Permeability test | 750 | 750 |  |  | 350 | 400 | 377 | 323 | k | Permeability test - Gradient of 54 psi
7.2 | Unloading | 750 | 750 |  |  | 400 | 350 | No flow | No flow | Vp, Vs, Potentiometer
7.3 | Permeability test | 750 | 750 |  |  | 350 | 400 | 377 | 323 | k | Permeability test - Gradient of 54 psi
7.3 | Unloading | 750 | 750 |  |  |  | 750
Loading Phase
Confining Pressure Ramping Rate | 15 psi/hr
Pore Pressure Ramping Rate | 15 psi/hr
S3/S1 | 0.8
Flow through permeability test

## Stresspath 1
Phase | Step | Time (hrs) | Cumulative Time (hrs) | Confining - Axial (psi) | Pore Pressure (psi) | Effective Stress | Measurements
Initial contact | 1 | 6.6667 | 6.6667 | 100 | 0 | 100 | Potentiometer - Initial sample length
Loading + Pore Pressure Ramping | 2 | 10 | 16.6667 | 250 | 115 | 135 | Potentiometer, Velocity, Permeability
Unloading | 4 | 2.3333 | 19 | 250 | 150 | 100 | Potentiometer, Velocity, Permeability
Draining | 5 | 2.3333 | 21.3333 | 250 | 115 | 135 | Potentiometer, Velocity
Loading | 6 | 16.6667 | 38 | 500 | 115 | 385 | Potentiometer, Velocity, Permeability
Unloading | 8 | 12.3333 | 50.3333 | 500 | 300 | 200 | Potentiometer, Velocity, Permeability
Draining | 9 | 4.6667 | 55 | 500 | 230 | 270 | Potentiometer, Velocity
Loading | 10 | 16.6667 | 71.6667 | 750 | 230 | 520 | Potentiometer, Velocity, Permeability
Unloading | 12 | 14.6667 | 86.3333 | 750 | 450 | 300 | Potentiometer, Velocity, Permeability
Unloading | 12 | 6.6667 | 93 | 750 | 550 | 200 | Potentiometer, Velocity, Permeability
Draining | 13 | 13.6667 | 106.6667 | 750 | 345 | 405 | Potentiometer, Velocity
Loading | 14 | 16.6667 | 123.3333 | 1000 | 345 | 655 | Potentiometer, Velocity, Permeability
Unloading | 16 | 17 | 140.3333 | 1000 | 600 | 400 | Potentiometer, Velocity, Permeability
Unloading | 17 | 6.6667 | 147 | 1000 | 700 | 300 | Potentiometer, Velocity, Permeability
Unloading | 18 | 6.6667 | 153.6667 | 1000 | 800 | 200 | Potentiometer, Velocity, Permeability
Draining | 19 | 22.6667 | 176.3333 | 1000 | 460 | 540 | Potentiometer, Velocity
Pore Pressure Increase Rate | 15 psi/hr
Confining Pressure Increase Rate | 15 psi/hr
Draining Pressure Decrease Rate | 15 psi/hr

## Stresspath 2
Phase | Step | Time (hrs) | Cumulative Time (hrs) | Confining - Axial (psi) | Pore Pressure (psi) | Effective Stress | Measurements
Initial contact | 1 | 6.6667 | 6.6667 | 100 | 0 | 100 | Potentiometer - Initial sample length
Loading | 2 | 26.6667 | 33.3333 | 500 | 0 | 500 | Potentiometer, Velocity, Permeability
Loading | 3 | 33.3333 | 66.6667 | 1000 | 0 | 1000 | Potentiometer, Velocity, Permeability
Unloading | 4 | 13.3333 | 80 | 1000 | 200 | 800 | Potentiometer, Velocity, Permeability
Unloading | 5 | 13.3333 | 93.3333 | 1000 | 400 | 600 | Potentiometer, Velocity, Permeability
Unloading | 6 | 13.3333 | 106.6667 | 1000 | 600 | 400 | Potentiometer, Velocity, Permeability
Unloading | 7 | 13.3333 | 120 | 1000 | 800 | 200 | Potentiometer, Velocity, Permeability
Draining | 8 | 22.6667 | 142.6667 | 1000 | 460 | 540 | Potentiometer, Velocity, Permeability
Loading | 9 | 66.6667 | 209.3333 | 2000 | 460 | 1540 | Potentiometer, Velocity, Permeability
Pore Pressure Increase Rate | 15 psi/hr
Confining Pressure Increase Rate | 15 psi/hr
Draining Pressure Decrease Rate | 15 psi/hr

## Stresspath 3
Phase | Step | Time (hrs) | Cumulative Time (hrs) | Confining - Axial (psi) | Pore Pressure (psi) | Effective Stress | Measurements
Initial contact | 1 | 6.6667 | 6.6667 | 100 | 0 | 100 | Potentiometer - Initial sample length
Loading | 2 | 26.6667 | 33.3333 | 500 | 230 | 270 | Potentiometer, Velocity, Permeability
Loading | 3 | 33.3333 | 66.6667 | 1000 | 460 | 540 | Potentiometer, Velocity, Permeability
Unloading | 4 | 9.3333 | 76 | 1000 | 600 | 400 | Potentiometer, Velocity, Permeability
Unloading | 5 | 13.3333 | 89.3333 | 1000 | 800 | 200 | Potentiometer, Velocity, Permeability
Draining | 8 | 22.6667 | 112 | 1000 | 460 | 540 | Potentiometer, Velocity, Permeability
Loading | 9 | 66.6667 | 178.6667 | 2000 | 920 | 1080 | Potentiometer, Velocity, Permeability
Pore Pressure Increase Rate | 15 psi/hr
Confining Pressure Increase Rate | 15 psi/hr
Draining Pressure Decrease Rate | 15 psi/hr